## Sheet1
Story Title | Estimate | Vote Started | Voting Duration | Avg Voting Time | Fastest | Slowest
SRS - Update based off client meeting | 8 | 5/18/2022 4:07:27 AM | 0:02 | 0:01 | isaac | Sanjay
SRS - Move all UI content into SRS | 2 | 5/18/2022 4:09:17 AM | 0:00 | 0:00 | Jay | isaac
SRS - Formatting and proofreading | 3 | 5/18/2022 4:09:33 AM | 0:00 | 0:00 | Filipe | Jay
UI - student client login | 8 | 5/18/2022 4:10:04 AM | 0:00 | 0:00 | Filipe | Sanjay
UI - Pick Typeface / ICON Pack | 1 | 5/18/2022 4:10:41 AM | 0:00 | 0:00 | Jay | Sanjay
UI - UC login page | 3 | 5/18/2022 4:10:57 AM | 0:00 | 0:00 | Filipe | Sanjay
UI - UC client dashboard | 5 | 5/18/2022 4:11:29 AM | 0:00 | 0:00 | Filipe | isaac
UI - UC client assessment page | 8 | 5/18/2022 4:11:48 AM | 0:01 | 0:00 | Jay | Filipe
UI - UC client create assessment | 3 | 5/18/2022 4:12:35 AM | 0:01 | 0:00 | isaac | Jay
UI - student client dashboard | 5 | 5/18/2022 4:13:16 AM | 0:00 | 0:00 | Jay | isaac
UI - student client assessment page | 8 | 5/18/2022 4:13:38 AM | 0:00 | 0:00 | Jay | Sanjay
UI - Mock DESIGNG work | 20 | 5/18/2022 4:14:13 AM | 0:01 | 0:01 | isaac | Jay
Handover - create document template | 2 | 5/18/2022 4:15:09 AM | 0:00 | 0:00 | isaac | Filipe
Handover - Basic plan for handover | 3 | 5/18/2022 4:15:26 AM | 0:00 | 0:00 | isaac | Jay
Handover - Create tickets for next semester | 3 | 5/18/2022 4:15:50 AM | 0:00 | 0:00 | Jay | isaac
Handover - Workout blocker tickets for next semester | 3 | 5/18/2022 4:16:32 AM | 0:01 | 0:01 | Sanjay | Jay
Handover - Dependency Matrix | 1 | 5/18/2022 4:17:15 AM | 0:00 | 0:00 | isaac | Jay
Handover - Appsmith - UC client create assessment | 8 | 5/18/2022 4:17:31 AM | 0:00 | 0:00 | Jay | isaac
Handover - Appsmith - Student Client Dashboard | 8 | 5/18/2022 4:18:01 AM | 0:00 | 0:00 | Jay | Sanjay
Handover - Appsmith - UC client dashboard | 8 | 5/18/2022 4:18:19 AM | 0:00 | 0:00 | Sanjay | isaac
Handover - Appsmith - UC client assessment page | 5 | 5/18/2022 4:18:36 AM | 0:00 | 0:00 | Filipe | Jay
Handover - Generate test data for database | 5 | 5/18/2022 4:19:05 AM | 0:00 | 0:00 | isaac | Sanjay
Handover - Monorepo setup | 1 | 5/18/2022 4:19:22 AM | 0:00 | 0:00 | isaac | Filipe
Handover - database setup | 3 | 5/18/2022 4:19:52 AM | 0:00 | 0:00 | Filipe | Sanjay
Handover - Cloud setup of Appsmith/Postgres | 2 | 5/18/2022 4:20:08 AM | 0:00 | 0:00 | isaac | Filipe
Handover - planning poker for future tickets | 13 | 5/18/2022 4:20:41 AM | 0:00 | 0:00 | isaac | Sanjay
Handover - Introduction | 2
Handover - Appendix | 2
143